## Sheet1
0 Story ID | User Story | Acceptance Criteria (Test Case) - what happens for this to be "working" | Assignee | Notes | Sprint | Started on | Completed on | Test passed on | Reporter
PMB-01 | As a PM, I want to convey project details and needs accurately and quickly so that I may receive approval for my potential project as quickly as possible. | Intake form puts data into database | Briana | Completed | 3 |  |  |  | Joanna
PMB-02 | As PMO, I want to receive applications for potential project that have accurate and detailed responses that are consistent with the responses of other applications so that I have the ability to view new requests and schedule resourcing meetings and add it for discussion to the roadmap meeting | PMO have a view for pending projects | Briana | Completed | 4(Priority 1) |  |  |  | Joanna
PMB-03 | As a Stakeholder, I want a clear set steps to request resources from T&I so that I can get my products created. | Add a link to homescreen that goes to Wiki page showing high-level project process | Briana | Completed | 4(Priority 1) |  |  |  | Joanna
PMB-04 | As an executive, I want to quickly view the goals of a potential project so that I can determine where a potential project will fit into the roadmap and future goals of the CFPB. | TBD | C/B | Not started yet | 4(Priority 3) |  |  |  | Joanna
PMB-05 | As the PM Support Team, we want to receive accurate and consistent responses from intake forms so that we don’t have track down the sender for greater detail which prevents me from quickly categorizing and giving the potential project a prioritization score. | Intake forms have drop-downs | C/B | Completed | 4(Priority 1) |  |  |  | Joanna
PMB-06 | As a PM, I want to receive an on-screen validation so that I know my project is in the review process. | Confirmation screen | Briana | Completed | 3 |  |  |  | Joanna
PMB-07 | As a PM, I want to receive email confirmation that my project has been approved so that I can work on Gate 0 documentation . | Email created and sent | Chris | Not started yet | 4(Priority 3) |  |  |  | Joanna
PMB-08 | As PMO, I want to send a confirmation email to the PM so that the PM knows to continue to the next step in their project’s development. | Email created and sent | Chris | Not started yet | 4(Priority 3) |  |  |  | Joanna
PMB-09 | As a PM, I want complete data for gate review so that I convey important information about my project without having to go through a laborious process. | Gate doc. screen | Briana | Not started yet | 4(Priority 3) |  |  |  | Joanna
PMB-10 | As a PM, I want to use my PIN to login so that I can jump to a specific project. | Project ID functionality works | Chris | Moved to story 39 & 40 | 3 |  |  |  | Joanna
PMB-11 | As a stakeholder, I want to view the entire MPL so that I can see details on any project. | MPL view created | C/B | Completed | 4(Priority 1) |  |  |  | Joanna
PMB-12 | As a PM, I want to be able to quickly add statuses so that I can convey the concerns and achievement of my projects in a timely fashion. | Profile screen is created | C/B | Completed | 3 | 2015-07-30 |  |  | Joanna
PMB-13 | As a PM, I want to be able to quickly edit statuses so that I can convey the concerns and achievement of my projects in a timely fashion. | Profile screen can be edited | C/B | In progress | 4(Priority 2) |  |  |  | Joanna
PMB-14 | As a PM, I want to place the most pertinent information at the forefront of my page so that those who have the ability to address my concerns can easily view them. | This is potentially an algorithm to ensure that the most important alerts are at the top. | Chris | Completed | 4 |  |  |  | Chris
PMB-15 | As PMO, I want to quickly view a profile page for concerns which a PM might have so that I can quickly address the risk/issue to ensure the project remains on time to meet its launch date. | Create recent activity column | C/B | Completed | 4 |  |  |  | Chris
PMB-16 | As a Stakeholder and Executives, I want to easily view the progress of a project so that I can make decisions on time, resource, and financial expenses. | Details (dates) on left column are updated | C/B | Completed? | 4(Prioriity 1) |  |  |  | Chris
PMB-17 | As the Project Support Team, I want to quickly view the concerns and contact information so that we may easily track down a point of contact. | Details (contact info) on left column are updated- make name a link to AD email address | C/B | In progress | 4(Prioriity 1) |  |  |  | Chris
PMB-18 | As the Project Support Team, I want to receive more detailed information about a PMs Risk/Issues to ensure PMO and executives receive a detailed analysis of the situation that a project faces so that the response can be quick and effective. | Risk/Issue table | C/B | Completed | 3 |  |  |  | Chris
PMB-19 | As a PM, I want to add Risks easily so that I feel comfortable updating information about my project. | The ability to add Risks | C/B | Completed | 3 |  |  |  | Chris
PMB-20 | As a PM, I want to edit Risks easily so that I feel comfortable updating information about my project. | The ability to edit Risks | C/B | In progress | 4(Priority 2) |  |  |  | Chris
PMB-21 | As a PM, I want to update Issues easily so that I feel comfortable updating information about my project. | The ability to add Issues | C/B | Completed | 3 |  |  |  | Chris
PMB-22 | As a PM, I want to edit Issues easily so that I feel comfortable updating information about my project. | The ability to edit Issues | C/B | In progress | 4(Priority 2) |  |  |  | Chris
PMB-23 | As a PM, I want to add milestones easily so that I feel comfortable updating information about my project. | The ability to add milestones | C/B | Completed | 3 |  |  |  | Chris
PMB-24 | As a PM, I want to edit milestones easily so that I feel comfortable updating information about my project. | The ability to edit milestones | C/B | In progress | 4(Priority 2) |  |  |  | Chris
PMB-25 | As a PM, I want to add notes easily so that I feel comfortable updating information about my project. | The ability to add notes | C/B | Completed | 3 |  |  |  | Chris
PMB-26 | As a PM, I want to edit notes easily so that I feel comfortable updating information about my project. | The ability to edit notes | C/B | In progress | 4(Priority 2) |  |  |  | Chris
PMB-27 | As PMO, I want to view the progress of a project so that I can confirm that the project is meeting deadlines. | The ability to view the milestone table | C/B | Completed | 3 |  |  |  | Chris
PMB-28 | As PMO, I want to view projects that are almost finished so that I can expedite the completion of projects that are close to completion. | The ability to view the MPL table | C/B | Completed | 3 |  |  |  | Chris
PMB-29 | As the Project Support Team, I want to ensure that project status correlates to the timeliness of the project so that we can ensure PMO has accurate information on the health of a project. | The ability to view the edit history - Shouldn't this include mapping a time period to a color status? | C/B |  | 4(Priority 2) |  |  |  | Chris
PMB-30 | As PMO, I want be able to view the overall health of CFPB projects and commonalities and trends in projects so that I can address any underlying problems in the project development process. | Reporting: The ability to view a R/I Graphics | C/B | Completed-ish | 4(Priiority 2) |  |  |  | Chris
PMB-31 | As a Stakeholder, I want to view the health of projects that I may have interest in so that I can know the progress and potential concerns that might require my assistance | Reporting: The ability to view all Start & End dates for active projects(MPL view) | C/B |  | 4(Priority 2) |  |  |  | Chris
PMB-32 | As the Project Support Team, I want to view visuals of the overall progress and health of CFPB projects so that we can produce powerpoints and other infographics that may better convey the health of CFPB projects. | Reporting: The ability to view all constraints | C/B |  | 4(Priority 2) |  |  |  | Chris
PMB-33 | As a PM, I want to make quick updates to my gate review document so that I can prepare the necessary documentation for Gate review. | The ability to edit gate review doc | C/B |  | 4(Priority 3) |  |  |  | Chris
PMB-34 | As a user I want to be able to edit info. while in the table view(trying this feature in the Chris way) |  | Chris | Completed | 3 |  |  |  | Joanna
PMB-35 | As a user I want to be able to edit info. while in the table view(trying this feature in the Briana way) |  | Briana |  | 4 |  |  |  | Joanna
PMB-36 | As PMO support, I want to have the ability to add dates and outcomes to pending projects so we can track its status through the approval process | PMO can add approved/denied, resource (y or n), date, and roadmap data to pending projects view | Briana | Completed | 4(Priority 3) |  |  |  | Joanna
PMB-37 | As a stakeholder, I want stoplight reporting so I can quickly see project status | An icon shows red yellow or green for risk status | Briana | Completed | 4 |  |  |  | Joanna
PMB-38 | As a PM or PMO Support, I want to be able to access the PMbook system | Homepage is created | Briana | Completed | 3 |  |  |  | Joanna
PMB-39 | As a user I want to have the ability to search for my project directly from the homepage | Search by project ID on index.html | Chris | Completed | 3 |  |  |  | Joanna
PMB-40 | As a user I want to have the ability to search for a specific project | Search by project using search bar | Chris | Completed | 3 |  |  |  | Joanna
PMB-41 | Created Django navigation | Links have been made to connect html pages/they’ve been given URLs | Chris | Completed | 3 |  |  |  | Joanna
PMB-42 | Created database for data storage | Database is set up and organized | Chris | Completed | 3 |  |  |  | Joanna
PMB-43 | Created the data structures to support the views | Views show expected data for milestones, R&I, MPL, edit history and notes tables | Chris | Completed | 3 |  |  |  | Joanna
PMB-44 | As a PMO Support I would like to see all received applications |  | Briana | Completed |  |  |  |  | Joanna
PMB-45 | As a PMO member, I want to be able to see all the screens when I am projecting onto a screen | PMbook looks regular when projected | Briana | Not started yet | 4
PMB-46 | As PMO Support, I want a report showing the number of status reports received per week so that I can see which were reported on time without issues, on-time with issues, late or not received | Number of active project versus number reported (pie graph in upper left of page 3) | C/B | Completed | 4
PMB-47 | As PMO Support, I want a historgram of portfolio status showing both the number of active projects and the overall performance score for the projects (calculated by Green = 100, yellow = 50, red = 0, not received = 0, and on hold = N/A) so that I can see how the projects are performing relative to the number of active projects | histogram on the lower right of page 3 | C/B | Completed(?) | 4
PMB-48 | As PMO Support, I want to see the number of projects in red, yellow or green status organized by capability so that I can tell how each area is doing | number of red, yellow and green projects by capability area (stacked bar graph left side of slide 4) | C/B | Completed(?) | 4
PMB-49 | As a PMO Support, I want a single view of all projects and their risks and issues and associated comments for each so that I can pick out individual risks/issues to highlight in the report and tally each | manually generated list of top attention items per project (right side of slide 5) | C/B | Briana's part is started | 4
PMB-50 | As a PMO Support, I want a report with the numer of risks and issues organized by category, so that I can see which catgegories have the most number of problems | bar graph with number of yellow or red issues/risks organized by category (left side of slide 5) | C/B |  | 4
PMB-51 | As PMO Support, I want a list of all projects displaying the project ID, the project name, the Project Management, Business Owner, target date, the last three status reports, and key dependencies, so that I can build the risk and issues presentation quickly | projects organized by capability area | C/B | Briana's part is started - not organized by capability | 5